## Slide 1: Project Management Process
Risk Management
From “Keep Your Projects On Track”
http://www.drdobbs.com/184414727

## Slide 2: Risk Management
Usually performed
  at the start of a project,
  at the beginning of major project phases (such as requirements, design, coding and deployment), and
  when there are significant changes (for example, feature changes, target platform changes and technology changes).

## Slide 3: Risk Management
Four steps to risk management are
  risk identification,
  risk analysis,
  risk management planning and
  risk review

## Slide 4: 1) Risk Identification
the brainstorming session, consider :
  Weak areas, such as unknown technology.
  Aspects that are critical to project success, such as the timely delivery of a vendor's database software, creation of translators or a user interface that meets the customer's needs.
  Problems that have plagued past projects, such as loss of key staff, missed deadlines or error-prone software

## Slide 5: 1) Risk Identification
Collect up the stakeholder! Who?
Hold a brainstorming session, consider :
  Weak areas, such as unknown technology.
  Aspects that are critical to project success, such as the timely delivery of a vendor's database software, creation of translators or a user interface that meets the customer's needs.
  Problems that have plagued past projects, such as loss of key staff, missed deadlines or error-prone software

## Slide 6: 2) Risk Analysis
Make each risk item more specific. Risks like "Lack of management buy-in" and "People might leave" are too vague.
Split the risk into smaller, specific risks, such as
  "Manager Jane could decide the project isn't beneficial,"
  "The database expert might leave," and
  "The webmaster may be pulled off the project.“
Set priorities

## Slide 7: 2) Risk Analysis
Risk Items (Potential Future Problems Derived from Brainstorming) | Likelihood of Risk Item Occurring | Impact to Project if Risk Item Does Occur | Priority (Likelihood * Impact)
New operating system may be unstable. | 10 | 10 | 100
Communication problems over system issues. | 8 | 9 | 72
We may not have the right requirements | 9 | 6 | 54
Requirements may change late in the cycle. | 7 | 7 | 49
Database software may arrive late. | 4 | 8 | 32
Key people might leave. | 2 | 10 | 20
The Priority Scheme

## Slide 8: 3) Risk Management Planning
Risk Items (Potential Future Problems Derived from Brainstorming) | Actions to Reduce Likelihood | Actions to Reduce Impact if Risk Does Occur | Who Should Work on Actions | When Should Actions Be Complete | Status of Actions
New operating system may not be stable. | Test OS more. | Identify second OS. | Joe | 3/3/01 | 
Communica-tion problems over system issues. | Develop system interface document for critical interfaces. | Add replan milestone to realign the team's schedule with other areas. | Cathy | 5/6/01 | 
We may not have the right requirements. | Build prototype of UI. | Limit Initial product distribution | Lois | 4/6/01 | 

## Slide 9: 4) Risk Review
review your risks periodically,
check how well mitigation is progressing.
change risk priorities, as required
Identify new risks.
rerun the complete risk process if the project has experienced significant changes.
incorporate risk review into other regularly scheduled project reviews

## Slide 10: Risk Management
Time Effective!
  90 to 120 minutes for projects that are 12 to 60 person-months
  Control the length of the session by controlling the scope you choose,
  most sessions usually take less than two hours